ECB-UNRESTRICTED

Pre-Migration Schedule
for T2 Participants

T2-T2S Consolidation								6.09.2022

Version 1.0 Final

Version Control

| Version | Date | Author | Distribution | Explanation |
| --- | --- | --- | --- | --- |
| 0.1 | 3-06-2022 | ECB | MTRSG | Initial draft version shared with Central Banks |
| 0.2 | 10.06.2022 | ECB | TCCG | Second version shared with members of the TCCG. |
| 0.3 | 29.08.2022 | ECB | MTRSG | Third version with updated dates for T2P activities and minor corrections since v0.2 (ref. T2.PM.T2P.SOR) and editorial updates. |
| 1.0 | 06.09.2022 | ECB | MTRSG | Final version for distribution to T2 Participants |

Table of Contents

1	Introduction	4

2	Pre-requisites	4

3	Conditions	4

4	Timings	5

5	Reporting	5

6	Co-management	5

7	Pre-Migration activities	5

7.1	Business process model and notation	5

7.2	Activity tables	6

8	Reference documents	19

# Introduction

This Pre-Migration Schedule for T2 Participants provides an overview of the Pre-Migration stage, the pre-requisites, conditions, timings, and the detailed description of activities. Each of these activities are described through a set of pre-defined categories to help the user understand the various aspects related to the activity. This document is also complemented by a Business Process Model Notation (BPMN) diagram which provides a high-level view of activities (green indicates optional). Activities that take place beforehand by the operator and Central Banks.

# Pre-requisites

Prior to the start of the Pre-Migration stage, T2 Participants must have fulfilled the following:

- Participants connectivity to ESMIG in Production has been established and verified. T2Ps are recommended to not only test the connectivity to ESMIG but also the end to end connectivity to the various underlying services e.g. CRDM, CLM, RTGS. This can be verified by using the Probe pages for U2A (for more details please refer to the Connectivity guidelines).

- Participants have submitted their registration forms to their Central Bank by 1 July 2022. The registration form template has been distributed by Central Banks to their communities. Supporting documentation on how to complete the form is available in the TARGET Registration and On-boarding Guide.

# Conditions

The Pre-Migration stage in Production is characterized by an organised approach split into the following four phases:

- T2 Operator reference data capture for Central Banks

- Central Banks system access and reference data capture configuration for their own party

- Central Banks reference data capture for their participants

- T2 Participants system access and reference data configuration for their own party

As opposed to the community-based approach, which was applied for Pre-migration in UTEST in order to advance and optimise the start of the UT stage a community level, the organised approach has set dates defined for the planned start and completion of the four phases. These harmonised dates were defined at Eurosystem level with the purpose to organise and monitor the progress of all participating communities within scheduled durations. These durations are based on the experiences from Central Bank Testing and User Testing.

T2 Participants can begin their system access and reference data configuration once their Central Bank has captured the necessary data for their party and created the required admin users (based on the provided Registration Form). Each Central Bank will communicate the expected completion of the reference data capture for their participants and the start date for the T2P activities. The starting date for the first batch of T2 Participants is the same across all communities. However, some Central Banks may plan additional subsequent batches of party creations at their discretion. This may be due to the size of their community or select participants readiness. The timings are elaborated in section 4 below. It is the responsibility of the Central Banks with additional batches to ensure that sufficient time is available for the participants to complete their configuration (e.g. create users, configure party and accounts) before the end of the Pre-Migration 27 October.

# Timings

The first batch of parties will be completed on 14 September. As described in section 3, some Central Banks may decide to have additional subsequent starting dates. In such cases, participants in batch 2-4 will be notified by their respective Central Bank.

| Batch | Start | Completion |
| --- | --- | --- |
| 1 | 14.09.2022 | 28.09.2022 |
| 2 | 28.09.2022 | 12.10.2022 |
| 3 | 12.10.2022 | 26.10.2022 |
| 4 | 18.10.2022 | 27.10.2022 |

Table 1 - T2P start and end of Pre-Migration activities

T2 Participants are advised to complete their Pre-Migration activities within the defined duration in the above table. This is to avoid a potential late peak in activities and required support for the Central Banks and their National Service Desks.

# Reporting

T2Ps have to report to their Central Bank on the timely completion of their activities (format and frequency of reporting decided at CB level)

# Co-management

Co-managers are responsible for the timely and accurate configuration of their co-managees. A comprehensive guide on co-management requirements, responsibilities including examples are available in the Explainer on Co-Management (ref. link section 8)

# Pre-Migration activities

## Business process model and notation

The diagram below presents the sequence of activities to be carried out during the Pre-Migration stage. The activities are further detail in section 5.2.

Figure 1 - Business Process Model and Notation for T2P activities

## Activity tables

| ID | T2.PM.T2P.SA |
| --- | --- |
| Activity Name | System access |
| Activity Group | System access and registration data form verification (T2 participants) |
| Actor | T2 participant admin |
| Data configuration (A2A, U2A) | U2A – reaching the landing page and the T2 common components. |
| Description | In this activity the T2 participant admin will access CRDM, CLM and RTGS via the ESMIG portal. |
| Prerequisites | T2.PM.CB.PTY.ARC.CU The T2 participant has provided the registration form(s) with the required data. Hardware and software complies with the requirements as listed in the CRDM UHB section 1.2.1 Setup and login procedures |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.ARC.CU |
| Optional | No |
| Reference UDFS | N/A |
| Reference UHB | CRDM: 1.2.1 Setup and login procedures CRDM: 1.2.5 User Administration |
| Reconciliation means | U2A: T2 participant admins are directed to an initial page named ESMIG portal that ensures proper routing to the web applications the user has been granted to enter. Once the user has accessed CRDM, the GUI should show the expected menu screens, fields, properties and functions, buttons and icons. |
| Related privileges | T2 participant admin privileges (configured by the CB as requested in the registration form provided by the T2 participant to the CB) |
| Required role | AH ESMIG Access |

| ID | T2.PM.T2P.ARC.CU |
| --- | --- |
| Activity Name | Access Rights Configuration |
| Activity Group | System access and registration data form verification (T2 participants) |
| Actor | T2 participant admin |
| Data configuration (U2A) | U2A: Common Access Rights Management Users New Common Access Rights Management Grant/revoke roles New/edit Common Access Rights Management Certificate Distinguished Names New |
| Description | The T2 participant admin will configure the access rights at user level, in order to assign the appropriate roles to all users of given party with the following tasks: - Create and maintain user - Grant (and revoke) the (default and additional) roles - Create certificate DN - Create user certificate DN link |
| Prerequisites | T2.PM.T2P.SA |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.RFDV |
| Optional | No (Access rights configuration is required for all with own access. Exemptions can apply e.g for co-managees) |
| Reference UDFS | CRDM 1.2.2.1.4 User CRDM 1.2.2.3.2 Configuration of access rights at user level |
| Reference UHB | CRDM UHB v2.0 2.3.3 Access Rights 2.3.3.3 User – New/Edit Screen 2.3.3.5 Certificate Distinguished Name – New Screen 2.3.3.5 Certificate Distinguished Name Links – New Screen 2.3.3.15 Grant/Revoke Role – New/Edit Screen |
| Reconciliation means | The participant Admin can go to Common Access Rights Management Users and check the search/list screen to verify the user was created. Click on the users details to verify the role assigned to the user. |
| Related privileges | Create Certificate Distinguish Name Create User Create User Certificate Distinguish Name Link User Certificate DN Link Query Access Rights Query Update User Privilege Query |
| Required role | AH ESMIG Access AH Access Rights Admin Party Administrator |

| ID | T2.PM.T2P.RFDV |
| --- | --- |
| Activity Name | Registration form data verification |
| Activity Group | System access and registration data form verification (T2 participants) |
| Actor | T2 participant user |
| Data configuration (A2A, U2A) | U2A: |
| Description | The T2 participant user will verify that the data visible in the system matches the data input from the registration form(s). This includes - Main information, general information on the Party; - Technical addresses, to define the Distinguished Names (DNs) that are authorized by the Party for the different services; - Service Link/s, to determine the participation type in the different services; - Information dedicated to specific TARGET services, that is defined at the Party level; - Invoice configuration, for completing the information needed for the billing set-up; |
| Prerequisites | The T2 participant admin has completed system access and created the users who will verify the registration form data in the system. T2.PM.T2P.ARC.CU |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.RC |
| Optional | No |
| Reference UDFS | N/A |
| Reference UHB | N/A |
| Reconciliation means | The T2 participant admin user can verify and confirm that all data provided in the registration form is present in the system. |
| Related privileges | Relevant query privileges (depends on the Reference Data that needs to be verified), e.g: System Entity Query Party Reference Data Query Party-Service Link List Query Cash Account List Query Authorised Account User Query |
| Required role | AH ESMIG Access AH CRDM Reader |

| ID | T2.PM.T2P.RC |
| --- | --- |
| Activity Name | Routing configuration |
| Activity Group | Party configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (U2A) | U2A: Common Network Configuration Routing New Common Network Configuration DN-BIC Routing New |
| Description | Routing configurations specify the technical elements that are used to send a given outgoing message to the relevant actor. The routing configuration allows the setting up of either a default routing which is used when no specific conditions are defined for a party and a specific outgoing message or dedicated routings for specific outgoing messages. This configuration has to be done for every network service e.g. message store and forward etc. Each T2 participant is responsible for maintaining the reference data for their DN-BIC routing links (only applicable to RTGS message flows). For Inbound communication, different DNs can be linked to different BICs and vice versa. In the outbound case, the same BIC can only be linked to a single DN. However different BICs can still be linked to the same DN. If set to Outbound, a DN can only be linked to no more than one BIC. |
| Prerequisites | T2.PM.T2P.ARC.CU |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.MSG.RC |
| Optional | No, except for U2A only users |
| Reference UDFS | CRDM UDFS v2.2 1.2.1 Connectivity |
| Reference UHB | CRDM 2.3.6.4 Routing 2.3.6.1 Distinguished Name – BIC Routing – Search/List Screen 2.3.6.2 Distinguished Name – BIC Routing – New/Edit Screen) 3.4.1.5 Create a Distinguished Name-BIC routing configuration |
| Reconciliation means | U2A: Users can go to Common Network Configuration Routing Search and enter any known search criteria to view the list of routing between party and services. Common Network Configuration DN-BIC Routing enter search criteria to display a list of DN-BIC couples matching the entered search criteria. |
| Related privileges | Create Routing Create DN-BIC routing, Routing list query Update Routing Update DN-BIC routing, DN BIC Routing query. |
| Required role | AH ESMIG Access AH CRDM Configuration Manager AH Access Rights Admin AH CRDM Reader |

| ID | T2.PM.T2P.MSG.RC |
| --- | --- |
| Activity Name | Report Configuration |
| Activity Group | Party Configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (U2A) | U2A: Common Messages and Reports Report Configuration New |
| Description: | The T2 participant user will configure the reports that the T2 participant wants to receive Note: users who wish to receive the RTGS directory on 1 November must set the valid from date of their Report configuration to 01.11.2022. |
| Prerequisites | T2.PM.T2P.RC |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.MSG.RSC |
| Optional | No |
| Reference UDFS | CRDM 1.3.7. Report configuration CLM 3.2.4 Messaging (Report configuration) 5.7.2 CLM report generation RTGS 3.2.4 Messaging (Report configuration) 5.6.2 RTGS report generation |
| Reference UHB | CRDM UHB v2.0 3.6.1 Report Management 3.6.1.1 Create a New Report Configuration |
| Reconciliation means | U2A: Users can go to Common Messages and Reports Report Configurations Search and enter any known search criteria to view the list of report configuration. Select the relevant row and check the details to verify the data input was correctly captured. (CRDM UHB 3.5 Reports) |
| Related privileges | Report configuration list query Report configuration details query Create report configuration Update report configuration |
| Required role | AH ESMIG Access AH CRDM Configuration Manager AH CRDM Reader |

| ID | T2.PM.T2P.MSG.RSC |
| --- | --- |
| Activity Name | Message subscription rule set configuration |
| Activity Group | Party configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (A2A, U2A) | Common Messages and Reports Message Subscription Rule Set New |
| Description: | The T2 participant user can configure the specific set of messages it wants to receive from individual services and components for T2 participants and accounts. Each message subscription rule set is defined by the following elements: - the name and the description of the message subscription rule set; - the service to which the Message Subscription Rule Set shall be applied for. - a validity period, specified by a mandatory initial date of validity and an optional final date of validity; - a set of subscribing interested parties to which the relevant service or component sends all the messages matching the rule set; |
| Prerequisites | T2.PM.T2P.MSG.RC |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.MSG.MSC |
| Optional | No, except for U2A only users |
| Reference UDFS | CRDM UDFS v2.2 1.3.5 – Message subscription configuration |
| Reference UHB | CRDM UHB v2.0 2.3.4.1 Message Subscription Rule Sets – Search/List Screen 2.3.4.2 Message Subscription Rule Set – Details Screen Context of Usage |
| Reconciliation means | U2A: Users can go to Common Messages and Reports MSRS Search and enter any known search criteria to view the list of message subscription rule sets. Select the relevant row and check the details to verify the data input was correctly submitted. |
| Related privileges | Create Message Subscription Rule Set Message subscription rule set details query Delete message subscription rule set Message subscription rule list query Update message subscription rule Delete message subscription rule |
| Required role | AH ESMIG Access AH CRDM Configuration Manager AH CRDM Reader |

| ID | T2.PM.T2P.MSG.MSC |
| --- | --- |
| Activity Name | Message subscription rules |
| Activity Group | Party configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (U2A) | U2A: Common Messages and Reports MSRS Search Details New Message Rule |
| Description: | The T2 participant user will set up message subscription rules, to be connected to an existing message subscription rule set.for the T2P’s parties and accounts. |
| Prerequisites | T2.PM.T2P.MSG.RSC |
| Next activity (i.e. activities for which this is a prerequisite) | N/A |
| Optional | No (except for U2A only) |
| Reference UDFS | CRDM UDFS v2.2 1.2.3 Message subscription 4.5.3.8 Message Subscription Rule - New |
| Reference UHB | CRDM UHB v2.0 2.3.4.1 Message Subscription Rule Sets – Search/List Screen 2.3.4.4 Message Subscription Rule – New/Edit Screen 4.1.15 Message Subscription Rule |
| Reconciliation means | U2A: User can go to Common Messages and Reports Message Subscription Rules Set Search and enter any know search criteria to view the list of rule sets. Select the rules set to which the rule was added, then click on details to verify that the rule was correctly captured in the rules set. |
| Related privileges | Message subscription rule set list query Message subscription rule set details query Message subscription rule list query Update Message Subscription Rule Set and Message Subscription Rule Set List Query |
| Required role | AH ESMIG Access AH CRDM Configuration Manager AH CRDM Reader |

| ID | T2.PM.T2P.DCA.AC |
| --- | --- |
| Activity Name | CLM and RTGS accounts configuration |
| Activity Group | Party configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (A2A, U2A) | U2A: COMMON Cash Limits New COMMON Cash Cash Accounts Search click on New or Edit button (to configure the Account Threshold) A2A: ModifyLimit (camt.011) |
| Description | The T2 participant user will configure: Limit Standing Order for Limit (bilateral/multilateral) Liquidity Transfer Order Account Threshold Configuration: Payment Bank users can only edit floor/ceiling attributes for Cash Accounts under their datascope and for the ones for which they have been defined as Co-Manager. Please note. - Minimum amount for a standing order for limit is EUR 1,000,000 - Setting to “0“ of the amount of a standing order for limit has a similar effect as the deletion of a standing order for limit. |
| Prerequisites | T2.PM.CB.PTY.RFDV |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.DCA.SOR |
| Optional | Yes |
| Reference UDFS | CRDM UDFS v2.2 1.3.3.3. Description of the entities/1.Cash account 1.3.3.3. Description of the entities/2. Limit 1.3.3.3. Description of the entities/3. Standing order for Limit 1.3.3.3. Description of the entities/5. Liquidity Transfer Order 1.3.3.3. Description of the entities/7. Account Threshold Configuration 3.1.1.7. ModifyLimit (camt.011) |
| Reference UHB | CRDM UHB v2.0 2.3.2.3 Cash Account 2.3.2.5 Limit |
| Reconciliation means | U2A: Users can go to COMMON Cash Standing/Predefined Liquidity Transfer Order Search and enter any known search criteria to view the list of standing liquidity transfer orders. User can go to COMMON Cash Limits Search and enter any known search criteria to view the list of configured limits related to the cash accounts. A2A: Users will receive a Receipt(camt.025) in return from the camt.024 message. Users will receive a Receipt(camt.025) in return from the camt.011 message. |
| Related privileges | Create Liquidity Transfer Order Update Liquidity Transfer Order Create Limit Update Limit Cash Account list query Cash Account reference data query DCA_UpdateT2SDedicatedCashAccount |
| Required role | AH ESMIG Access AH CRDM Liquidity Manager AH CRDM Reader |

| ID | T2.PM.T2P.SOR |
| --- | --- |
| Activity Name | Standing Order (T2 participants CLM and RTGS accounts) |
| Activity Group | Party configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (A2A, U2A) | U2A: COMMON Cash Standing Order for Reservation New U2A: COMMON Cash Standing/Predefined Liquidity Transfer Order New A2A: ModifyStandingOrder (camt.024) |
| Description | Creation of a new Standing Order for a T2 participants CLM and RTGS accounts, specifying the priority, amount, cash account number, and Valid To and From. User can create standing orders with the following type: - Predefined - Standing - Rule-based floor - Rule-based ceiling Note: T2Ps must close their current T2S Standing Orders to TARGET2 as of business day 21/11. |
| Prerequisites | T2.PM.CB.PTY.DCA.AC |
| Next activity (i.e. activities for which this is a prerequisite) | T2.PM.T2P.AMGC |
| Optional | Yes |
| Reference UDFS | RTGS UDFS v2.2 3.1 Parties and Accounts) 3.2 Accounts structure and functionalities 3.2.3 Functionalities CRDM UDFS v2.2 1.3.3.3. Description of the entities/1.Cash Account 3.1.1.1. ModifyStandingOrder (camt.024) |
| Reference UHB | CRDM UHB v2.0 2.4.1.13 Standing Order for Reservation – New/Edit Screen 2.3.2.8 Standing/Predefined Liquidity Transfer Order – Search/List Screen 2.3.2.9 Standing/Predefined Liquidity Transfer Order – Details Screen 2.3.2.10 Standing/Predefined Liquidity Transfer Order – New/Edit Screen |
| Reconciliation means | U2A: Users can go to T2 Cash Standing Orders for Reservation Search and enter any known search criteria to view the list of standing orders for reservation. A2A: Users will receive a Receipt(camt.025) in return from the camt.024 message. |
| Related privileges | Create Standing Order for Reservation Standing Order for Reservation List Query Standing Order for Reservation Details Query Update Standing Order for Reservation |
| Required role | AH ESMIG Access AH CRDM Liquidity Manager AH CRDM Reader |

| ID | T2.PM.T2P.AMGC |
| --- | --- |
| Activity Name | Account Monitoring Group Configuration |
| Activity Group | Party configuration (T2 participant) |
| Actor | T2 participant user |
| Data configuration (U2A) | U2A: T2 Cash Account Monitoring Group New |
| Description | An Account Monitoring Group is an optional group of accounts (MCA(s) and DCA(s)). It grants a collective view over the liquidity of the involved accounts to payment banks. An Account Monitoring Group is used for liquidity monitoring purposes of payment banks; they are not used for the context of payment orders or liquidity transfer orders settlement. The leader party of the Account Monitoring Group can see the liquidity of all included accounts while the other participants of the Account Monitoring Group can only see the liquidity of their accounts. Payment banks can set up an Account Monitoring Group and specify the name of this group. The Account Holder, which sets up the Account Monitoring Group, is defined as leader party of the Account Monitoring Group. Each payment bank can then optionally add MCAs in his data scope to the Account Monitoring Group. All actions (set up, modify, delete) become effective as of the next business day or on the activation date. |
| Prerequisites: Internal activities | T2.PM.CB.PTY.MCA.CLM T2.PM.CB.PTY.DCA.RTGS |
| Next activity (i.e. activities for which this is a prerequisite) | None |
| Optional | Yes |
| Reference UDFS | CRDM UDFS v2.2 1.2.4. Graphical user interface CLM UDFS 3.4 Type of group |
| Reference UHB | CRDM UHB v2.0 2.4.1.3 - Account Monitoring Group |
| Reconciliation means | U2A: Users can go to T2 Cash Account Monitoring Group Search and enter any known search criteria to view the list of Account monitoring group names To view the details, select the row with the group name that was created, click on Details on the right side of the search list and verify that the data submitted corresponds to the list of details. |
| Related privileges | Create Account Monitoring Group Account Monitoring Group query Update Account Monitoring Group Account Monitoring Group Details Query |
| Required role | AH ESMIG Access AH CRDM Configuration Manager AH CRDM Reader AH CRDM AMG Manager |

# Reference documents

T2 Migration, Testing and Readiness Strategy

CRDM User Detailed Functional Specifications

CRDM User Handbook

Explainer on CRDM terms and concepts for T2

Explainer on Co-Management

Additional reference documents are available on the ECB website for professional use