## Release T2 R2027.JUN Calendar
Line | Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | EAC | UTEST | PROD | FW | Other | Comments
1 | 18 | Day | 2026-04-29 | 2026-04-29 | Release scope | T2-WG proposes baseline release scope and STP for T2 R2027.JUN
2 | 20 | Day | 2026-05-15 | 2026-05-15 | Release scope | Scope baseline & STP for T2 R2027.JUN approved by the MIB
3 | 50 | Day | 2026-12-09 | 2026-12-09 | Documentation | Publication for non-binding XSDs in MyStandards and Readiness Portal in T2 open community (T2 R2027.JUN)
4 | 5 | Day | 2027-01-26 | 2027-01-26 | Documentation | Publication for binding XSDs in MyStandards and Readiness Portal in T2 open community (T2 R2027.JUN) | [5 empty] | 9 business days before EAC deployment (OGPF)
5 | 5 | Day | 2027-01-29 | 2027-01-29 | Release scope | Publication date for draft Scope defining set of documents (CLM, RTGS, DWH, Common Components) related to T2 R2027.JUN
6 | 6 | Day | 2027-02-05 | 2027-02-05 | Release deployment | Deployment of Package 1 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
7 | 7 | Week | 2027-02-08 | 2027-03-15 | Release testing | T2 R2027.JUN release testing in EAC | E
8 | 8 | Day | 2027-02-18 | 2027-02-18 | Release deployment | Deployment of Package 2 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
9 | 10 | Day | 2027-03-05 | 2027-03-05 | Release deployment | Deployment of Package 3 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
10 | 11 | Day | 2027-03-12 | 2027-03-12 | Release scope | Latest publication date for updated Scope defining set of documents (CLM, RTGS, DWH, Common Components)
11 | 12 | Day | 2027-03-15 | 2027-03-15 | Documentation | Service Transition Status Report (STSR) for T2 R2027.JUN in Pre-Production (cut-off and delivery T2-WG)
12 | 12 | Day | 2027-03-15 | 2027-03-15 | Documentation | T2-WG approval of the security assessment and STSR for T2 R2027.JUN in Pre-Production
13 | 12 | Day | 2027-03-16 | 2027-03-16 | Reporting | T2-WG Go / No-go decision to deploy T2 R2027.JUN to Pre-Production | [5 empty] | 8 business days before UTEST deployment
14 | 12 | Day | 2027-03-16 | 2027-03-16 | Documentation | Delivery of T2 R2027.JUN CR Detailed Assessments to ECB Compliance Team for GDPR check | [5 empty] | This step is performed in view of the yearly reporting to the MIB in terms of GDPR by the ECB Compliance Team.
15 | 12 | Day | 2027-03-19 | 2027-03-19 | Release deployment | Deployment of Package 4 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
16 | 14 | Day | 2027-04-02 | 2027-04-02 | Release deployment | Deployment of Package 5 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
17 | 14 | Day | 2027-04-02 | 2027-04-02 | Release deployment | Start release deployment to Pre-production |  | U
18 | 14 | Day | 2027-04-02 | 2027-04-02 | Release deployment | Deployment of Package 1-5 to Pre-Production |  | U |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | 14 | Day | 2027-04-03 | 2027-04-03 | Documentation | Delivery of the T2 R2027.JUN Statement of IT Security (STITS) | [5 empty] | Delivery at the latest 10 weeks before PROD deployment
20 | 15 | Day | 2027-04-05 | 2027-04-05 | Release testing | Start of testing of T2 R2027.JUN scope elements in Pre-Production
21 | 15 | Week | 2027-04-05 | 2027-05-25 | Release testing | T2 R2027.JUN Release testing in Pre-Production |  | U
22 | 16 | Day | 2027-04-14 | 2027-04-14 | Documentation | Release risk assessment | [5 empty] | T2 Evolution and Operations teams are producing this assessment at the latest 8 weeks before PROD deployment
23 | 16 | Day | 2027-04-16 | 2027-04-16 | Release deployment | Deployment of Package 6 to EAC and Pre-Production | E | U |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
24 | 17 | Day | 2027-04-23 | 2027-04-23 | Release deployment | Deployment of Package 7 to EAC and Pre-Production | E | U |  |  |  | RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
25 | 18 | Day | 2027-04-30 | 2027-04-30 | Release deployment | Deployment of Package 8 to EAC and Pre-Production | E | U |  |  |  | RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
26 | 19 | Day | 2027-05-07 | 2027-05-07 | Release deployment | Deployment of Package 9 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
27 | 20 | Day | 2027-05-14 | 2027-05-14 | Release deployment | Deployment of Package 10 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
28 | 21 | Day | 2027-05-21 | 2027-05-21 | Release deployment | Deployment of Package 11 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
29 | 22 | Day | 2027-05-25 | 2027-05-25 | Release testing | End of testing of T2 R2027.JUN scope elements in Pre-Production |  | U
30 | 22 | Day | 2027-05-25 | 2027-05-25 | Reporting | Service Transition Status Report (STSR) for T2 R2027.JUN in Production (cut-off and delivery to T2-WG)
31 | 22 | Day | 2027-05-26 | 2027-05-26 | Reporting | T2-WG recommends the release deployment to Production | [5 empty] | 11 business days before PROD deployment (OGPF)
32 | 22 | Day | 2027-05-28 | 2027-05-28 | Release deployment | Deployment of Package 12 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
33 | 23 | Day | 2027-06-02 | 2027-06-02 | Reporting | MIB approves the release deployment to Production | [5 empty] | 8 business days before PROD deployment (OGPF)
34 | 23 | Day | 2027-06-04 | 2027-06-04 | Release deployment | Deployment of Package 13 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
35 | 24 | Weekend | 2027-06-12 | 2027-06-12 | Release deployment | Start release deployment to Production |  |  | P
Formulas:
Week number = WEEKNUM([Start Date])